## WBS
WBS No. | Task No. | Task Description | Duration | Work | Prerequisite Tasks | Resources | Start Date | End Date
1 - Initial Planning | 1 | Project Definition | 3 | 6 |  | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Architect / Data Modeler / DBA ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist | 2017-04-06 | 2017-04-09
| 2 | Project Planning & Management | 9 | 18 | 1 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-04-09 | 2017-04-18
| 3 | Program Planning & Management | 6 | 12 | 2 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-04-18 | 2017-04-24
| 4 | Business Requirements Definition | 13 | 26 | 3 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-04-24 | 2017-05-07
2 - DW/BI Technical Architecture | 5 | Application Architecture Design | 10 | 80 | 4 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-05-07 | 2017-05-17
| 6 | Branch Analysis (Demographics, Supply and Demand Analysis) | 10 | 80 | 4 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-05-17 | 2017-05-27
| 7 | Create Inventory Ordering Policies | 10 | 80 | 6 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-05-27 | 2017-06-06
| 8 | Manage Metadata | 9 | 72 | 5 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-06-06 | 2017-06-15
| 9 | Implement Tactical Security Measures | 9 | 72 | 5 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-06-15 | 2017-06-24
| 10 | Develop Strategic Security Plan | 7 | 56 | 9 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-06-24 | 2017-07-01
| 11 | Create Infrastructure Plan | 5 | 40 | 10 | Project Manager Technical Architect / Tech Support Specialist | 2017-07-01 | 2017-07-06
| 12 | Inventory Ordering Policy Installation | 5 | 40 | 7 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-07-06 | 2017-07-11
3 - Implementation | 13 | Dimensional Data Model Design | 19 | 76 | 11 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-07-11 | 2017-07-30
| 14 | Physical Database Design | 11 | 44 | 13 | Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-07-30 | 2017-08-10
| 15 | Physical Database Implementation | 7 | 28 | 14 | Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-08-10 | 2017-08-17
| 16 | ETL System Design | 14 | 56 | 15 | Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-08-17 | 2017-08-31
| 17 | ETL System Development | 13 | 52 | 16 | Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-08-31 | 2017-09-13
| 18 | BI Application Design | 9 | 36 | 14 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-09-13 | 2017-09-22
| 19 | BI Application Development | 16 | 64 | 18 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-09-22 | 2017-10-08
4 - Deployment & Operations | 20 | Pre-Deployment Testing | 5 | 40 | 19 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-10-08 | 2017-10-13
| 21 | Data and Process Testing | 6 | 48 | 20 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Lead Tester Educator | 2017-10-13 | 2017-10-19
| 22 | Performance Tuning | 7 | 56 | 21 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Lead Tester Data Mining / Stats Specialist Educator | 2017-10-19 | 2017-10-26
| 23 | Other Testing | 3 | 24 | 22 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Educator | 2017-10-26 | 2017-10-29
| 24 | System Deployment | 6 | 48 | 23 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Data Mining / Stats Specialist Educator | 2017-10-29 | 2017-11-04
| 25 | User Facing Deployment | 4 | 32 | 24 | Business Users Business Sponsor / Business Driver DW/BI Director / Program Project Manager Business Project Lead Business Analysts Data Steward / QA Analyst Data Architect / Data Modeler / DBA Metadata Manager ETL Architect / ETL Developer BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist Security Manager Data Mining / Stats Specialist Educator | 2017-11-04 | 2017-11-08
| 26 | Back Room Operations | 4 | 32 | 25 | Project Manager Data Architect / Data Modeler / DBA | 2017-11-08 | 2017-11-12
| 27 | Front Room Operations | 4 | 32 | 25 | Business Users DW/BI Director / Program Project Manager Business Analysts BI Architect / App Developer / Portal Developer Technical Architect / Tech Support Specialist | 2017-11-12 | 2017-11-16
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]